## Sheet1
ITSC-3155 Software Engineering
Sprint Backlog
Story Tasks | Story Point | Assigned to | Estimated Effort | Day1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | Status | SPRINT REVIEW
Have an ingredient inventory | 8 | Joey | 19 | 7.5 | 6 | 11 | 1 | 1 | 0 | Done
Create Resource Management table |  |  | 7 | 5 | 3 | 0 | 0 | 0 | 0 |  | 0
Add resources |  |  | 8 | 1 | 1 | 5 | 0 | 1 | 0 |  | 0
Remove resources |  |  | 1 | 0.5 | 0 | 3 | 0 | 0 | 0 |  | 0
Get Resources |  |  | 3 | 1 | 2 | 3 | 1 | 0 | 0 |  | 0
Implement a user feedback feature | 13 | Eli | 14 | 12 | 11.5 | 2.5 | 3 | 1 | 0 | Done
Customer can leave reviews |  |  | 3 | 3 | 0.5 | 0.5 | 0 | 0 | 0 |  | 1
Employees can read reviews |  |  | 3 | 5 | 5 | 1 | 1 | 1 | 0 |  | 0
Employees can see average review rating |  |  | 5 | 2 | 5 | 0 | 1 | 0 | 0 |  | 1
Customers can update and delete reviews |  |  | 3 | 2 | 1 | 1 | 1 | 0 | 0 |  | 1
Order operations | 5 | Will | 19.5 | 8.5 | 3.5 | 3.5 | 4 | 1 | 0 | Done
Read all orders |  |  | 8 | 6 | 0 | 0 | 0 | 0 | 0 |  | 0
Create and Delete orders |  |  | 8 | 1 | 3 | 3 | 3 | 0 | 0 |  | 0
Update orders |  |  | 1.5 | 1 | 0.5 | 0.5 | 1 | 1 | 0 |  | 0
Read one order |  |  | 2 | 0.5 | 0 | 0 | 0 | 0 | 0 |  | 3
Order from the menu | 8 | Connor | 21 | 12 | 13 | 13 | 5 | 2 | 0 | Done
Allow from user input from api, and push to order table |  |  | 9 | 4 | 2 | 2 | 1 | 1 | 0 |  | 0
Allow users to create new menus |  |  | 6 | 6 | 3 | 3 | 3 | 1 | 0 |  | 1
Allow users to see menus |  |  | 6 | 2 | 8 | 8 | 1 | 0 | 0 |  | 1
0
Allow users to put more than one type of payment | 4 | Bayli | 8 | 7 | 7 | 1.5 | 3.5 | 10 | 0 | Done
Create payment ids and customer ids |  |  | 2 | 1 | 1 | 1 | 0.5 | 1 | 0 |  | 1
Create option for different types of payments |  |  | 6 | 6 | 6 | 0.5 | 3 | 9 | 0 |  | 0
3
1
TOTAL |  |  | 81.5 | 47 | 41 | 31.5 | 16.5 | 15 | 0 |  | 14