## Sheet1
ITSC-3155 Software Engineering
Sprint Backlog
Story Tasks | Story Point | Assigned to | Estimated Effort | Day1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | Status | SPRINT REVIEW
Implement a promotional code feature | 8 | Joey | 19 | 7.5 | 6 | 11 | 1 | 1 | 0 | Done
See Promotions |  |  | 7 | 5 | 3 | 0 | 0 | 0 | 0 |  | 0
Make and remove Promotions |  |  | 8 | 1 | 1 | 5 | 0 | 1 | 0 |  | 0
Update promotions |  |  | 1 | 0.5 | 0 | 3 | 0 | 0 | 0 |  | 0
Apply promotions |  |  | 3 | 1 | 2 | 3 | 1 | 0 | 0 |  | 0
Track data analytics | 13 | Eli | 19 | 15 | 19.5 | 6.5 | 3 | 1 | 0 | Done
Report popular and unpopular dishes |  |  | 3 | 3 | 0.5 | 0.5 | 0 | 0 | 0 |  | 2
Get revenue and orders by date range |  |  | 3 | 5 | 5 | 1 | 1 | 1 | 0 |  | 0
Get daily revenue |  |  | 8 | 2 | 5 | 0 | 1 | 0 | 0 |  | 1
Get dishes with complaints |  |  | 5 | 5 | 9 | 5 | 1 | 0 | 0 |  | 1
See Order numbers and details | 5 | Will | 19.5 | 8.5 | 3.5 | 3.5 | 4 | 1 | 0 | Doing
Allow user to see order details |  |  | 8 | 6 | 0 | 0 | 0 | 0 | 0 |  | 0
Create operation for order details |  |  | 8 | 1 | 3 | 3 | 3 | 0 | 0 |  | 0
Update order details |  |  | 1.5 | 1 | 0.5 | 0.5 | 1 | 1 | 0 |  | 0
Delete order details |  |  | 2 | 0.5 | 0 | 0 | 0 | 0 | 0 |  | 3
Update the menu | 8 | Connor | 15 | 10 | 5 | 5 | 4 | 2 | 0 | Done
Create relationship between menu and inventory |  |  | 9 | 4 | 2 | 2 | 1 | 1 | 0 |  | 0
Allow user to update menus |  |  | 6 | 6 | 3 | 3 | 3 | 1 | 0 |  | 1
1
0
Have data regarding order history | 3 | Bayli | 17 | 16.5 | 16.5 | 6.5 | 7 | 13 | 0 | Done
Allow user to see past orders |  |  | 2 | 1 | 1 | 1 | 0.5 | 1 | 0 |  | 1
Allow user to delete past order data |  |  | 6 | 6 | 6 | 0.5 | 3 | 9 | 0 |  | 0
Allow user to delete past order data |  |  | 7 | 9 | 9 | 4 | 3 | 3 | 0 |  | 3
|  |  | 2 | 0.5 | 0.5 | 1 | 0.5 | 0 | 0 |  | 1
TOTAL |  |  | 89.5 | 57.5 | 50.5 | 32.5 | 19 | 18 | 0 |  | 14